## Title
CS 554 S/W Engineering In Class Project
Math Scramble/Sliding Tiles
| Members | Maxwell Garvey
Neeraja Budamagunta
Pratibha Natani
Seema Saijpaul

## Requirements
Math Scramble / Sliding Tiles | Mode 1
Develop an Android or iPhone game with two modes. The first allows users to define basic mathematic equations using digits 0 ‐ 9 and the addition, subtraction and multiplication operators. This application should be targeted towards a younger audience learning basic mathematics. Equations can be formed either horizontally from left to right or vertically from top to bottom. Equations must include either the "+", "‐" or "x" operators and the "=" symbol (i.e. 9 = 9 is not allowed). A candidate equation is submitted by dragging a finger across the screen. If the equation is valid, then points are added to the user's score. The line in blue would be worth five points. The same equations can be used exactly once (i.e. 2 + 3 = 5 and 5 = 3 + 2 represent the same equation). Players can form new equations by moving tiles around the board (see the diagram below). It must be possible to form at least one mathematical equation on a given board.
Mode 2
In the second mode, the users are presented with a random board of numbers from 1 to 24. In this mode, the board also contains the empty black tile. The users must order the numbers sequentially in ascending order. The black tile must either be in the top left or bottom right position. It must be possible to solve the puzzle. Players can either play alone or against a basic AI. This AI does not have to be particularly smart or fast, but it should be able to correctly order tiles in a reasonable amount of time. The AI difficulty setting should be adjustable. Please feel free to search the scientific literature for algorithms for the twenty four puzzle or sliding puzzle. Please cite any references used. Variations on this mode should be possible. Allow users to select from 2 x 2, 3 x 3, 4 x 4 or 5 x 5 grids. The first mode can only be played on a 5 x 5 grid

## Iteration 1
Process Model
Agile Software Development using Iterative Model
Iteration 1
Goals
1. Understand and Analyze the requirements,android SDK
2. Develop the UI for the home page
3. Develop UI for Mode 1 of Sliding Tiles
4. Set up code repository
5. Functionality for creating the 5*5 tile grid
6. Functionality for ability to slide the created tiles using one blank tile
7. Analyze on testing methodology
Responsibilities and Roles
Project Member | Responsibilty | Role
Seema/Pratibha | 1.Develop UI components for Home screen 2.Develop UI for Mode 1 | Developer
Neeraja | 1. Set up code repository 2.Merge code developed for Home and Mode 1 3.Co-ordinate and updates for presentation 1 | Manager
Maxwell | 1.Test the UI developed 2.Analyze on testing methodologies 3.Analyze on Junits provided by Android | Tester
Implementation
1. Completed set up of code repository at GitHub (https://github.com/saijpaul/Sliding-tiles-Project)
2. Completed Development and testing of UI for Home screen + Making Equations Screen(Mode 1)
3. Completed development and testing of functionality to slide tiles on making equations screen
Customer Reviews for Iteration 1
1. Update the images of buttons for mode 1/2 to make it look more like buttons rather than images.
2. Change help text to include picture clips for better understandability
3. Change the dimensions of tiles from rectangular to square
4. Remove the exit button from the home screen

## Iteration 2
Iteration 2
Goals
1.Implement changes according to customer review comments on home screen
2.Generate operators and numbers on the grid such that there is atleast one valid equation
3.Implement methodology to capture valid slide moves to submit an equation
4.Implement validation of submitted equations
5. Update score for each valid equation formed by user
6. Update code repository
Responsibilities and Roles
Project Member | Role
Seema | Developer/Tester
Neeraja | Developer/Tester
Maxwell | Manager/Tester
Pratibha | Developer/Tester
Implementation
1. Implemented changes to home screen according to customer review comments except addition of pictures in Help dialog box
2. Implemented UI changes to Make Equation Screen according to customer review comments
3. Completed the functionality to select equation on the screen
4. Implemented functionality of generating operators and numbers on the tiles in Make Equation Screen
5. Implemented functionality of validating and updating scores according to selected eqautions
6. Updated Code repository
Customer Reviews for Iteration 2

## Iteration 3
Iteration 2
Goals
1.Implement changes to UI
2.Implement functionality of Puzzle (Basic + AI)
3.Implement enhancement of sound effect in equation game
4. Testing and Bug Fixing
5. Update code repository
Responsibilities and Roles
Project Member | Role
Seema | Developer/Tester
Neeraja | Developer/Tester
Maxwell | Developer/Tester
Pratibha | Developer/Tester
Implementation
1. Implemented changes to UI(Changed color scheme completely + Addition of animated button for bothe modes + sound effect on correct and wrong equation)
2. Implemented basic mode 2 game
3. Implemented AI functionality but still need to integrate with the system
4. Updated Code repository